## READ ME
This quarterly status update form is used to provide an intial project schedule with your application for STP Shared Funding
and, if selected for the Active or Contingency program, to provide quarterly updates as required by the region's
Active Program Management policies.
If completing this form for the first time during a call for projects:
1. If you haven't already, start your eTIP application to receive a TIP ID
2. Note the TIP ID and Project Title used in your eTIP application in the <enter project name> and <enter TIP ID> fields on the Update form
3. Follow the Instructions for Initial submittals only section of the STP Project Quarterly Status Update Instructions
It is not necessary for sponsors of current active or contingency projects included in the FFY 2020-2020 STP Shared Fund Program or in an FFY 2021 - 2025
Council STP Local Program to submit a new form with their application for the FFY 2022-2026 STP Shared Fund. Those sponsors may utilize either their
December 2020 or March 2021 quarterly update. However, those sponsors must still attach their update to their new eTIP application.
TIP! If you're working on laptop or small screen, on the Update form you can select View > Freeze Panes > Unfreeze Panes to allow a larger number of input
rows to be visible on your screen.

## Update form
STP-Shared Fund Quarterly Status Update (projects processed through FTA)
Project: | <enter project name> |  |  |  | TIP ID: | <enter TIP ID>
UPDATE INFORMATION |  |  |  |  | PROJECT INFORMATION
| Completed By: | Date:
Initial Submittal |  | <mm/dd/yyyy> |  |  | Environmental Class of Action: |  | <class of action> |  | <status> |  | <approval date>
Most Recent Prior Update |  | <mm/dd/yyyy> |  |  | Environmental Approval: |  | <environmental approval type>
Current Update |  | <mm/dd/yyyy> |  |  | Current construction/implementation cost estimate: |  | <whole dollars>
Final "Actual" Dates |  | <mm/dd/yyyy> |  |  | Change in estimate since prior update: |  | <whole dollars> | <describe primary reason(s) for change>
MILESTONE INFORMATION
No changes from prior update
Phase Groups | Milestone (Shaded lines required for federally-funded phases only) | Initial Estimated Date (m/yyyy) | Complete? | Updated Estimated Date (m/yyyy) | Actual Date (m/d/yyyy) | Attachments (R - Required, O - Optional) | Sponsor/Implementer Comments |  |  | FTA Project and Construction Management Guidelines section reference
Project Development/ Pre-engineering | Systems Planning |  | <yes/no> | [6 empty] | 2.2.1
| Alternatives Analysis |  | <yes/no or n/a> | [6 empty] | 2.2.2
| Project Management Plan (PMP) |  | <yes/no or n/a> | [6 empty] | 2.2.3
| Environmental Assessment/Mitigation Plan |  | <yes/no or n/a>
| Design Control Plan |  | <yes/no or n/a>
| Real Estate Acquisition and Management Plan (RAMP) |  | <yes/no or n/a> | [6 empty] | 4.5.1
| Safety and Security Management Plan (SSMP) |  | <yes/no or n/a> | [6 empty] | 2.2.11
| Project Delivery and Procurement Plan |  | <yes/no or n/a> | [6 empty] | 2.2.6
| Environmental Planning |  | <yes/no or n/a> | [6 empty] | 2.2.7
| Section 4(f) evaluation |  | <yes/no or n/a> | [6 empty] | 2.2.7.3
| Section 106 (Historic Preservation) process |  | <yes/no or n/a> | [6 empty] | 2.2.7.4
| NEPA process initiated |  | <yes/no or n/a>
| NEPA process completed (ROD, FONSI, or CE determination) |  | <yes/no or n/a> | [6 empty] | 4.4
| Preliminary Design Drawings |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Preliminary Specifications and Design Standards |  | <yes/no or n/a>
| Preliminary Contract Packaging Plan |  | <yes/no or n/a>
| Preliminary Cost Estimates |  | <yes/no or n/a>
| Preliminary Contract Documents |  | <yes/no or n/a>
| Preliminary right-of-way plans |  | <yes/no or n/a>
| Preliminary utility plans |  | <yes/no or n/a>
| Preliminary third-party agreements and permits |  | <yes/no or n/a>
Engineering and Design | FTA grant application in TrAMS |  | <yes/no or n/a> |  |  | Copy of application (O) | <Enter temporary grant # here>
Federally-funded | FHWA to FTA transfer request to IDOT |  | <yes/no or n/a> |  |  | Copy of request letter (R)
| FTA grant approval |  | <yes/no or n/a> |  |  |  | <Enter FTA grant # here>
| Consulant selection |  | <yes/no or n/a>
| Final Design Drawings |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Final Specifications and Design Standards |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Final Contract Packaging Plan |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Final Cost Estimates |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Final Contract Documents |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Final right-of-way plans |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Final utility plans |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Final third-party agreements and permits |  | <yes/no or n/a> | [6 empty] | 2.3.2
| Final construction bid packages |  | <yes/no or n/a> | [6 empty] | 2.3.4
| Final construction management plan |  | <yes/no or n/a> | [6 empty] | 2.3.4
| Initital design review |  | <yes/no or n/a> | [6 empty] | 4.7.3.1
| Final verification |  | <yes/no or n/a> | [6 empty] | 4.7.3.2
ROW | FTA grant application in TrAMS |  | <yes/no or n/a> |  |  | Copy of application (O) | <Enter temporary grant # here>
None required | FHWA to FTA transfer request to IDOT |  | <yes/no or n/a> |  |  | Copy of request letter (R)
Federally-funded | FTA grant approval |  | <yes/no or n/a> |  |  |  | <Enter FTA grant # here>
| Consulant selection |  | <yes/no or n/a>
| Initiation |  | <yes/no or n/a>
| Negotiations |  | <yes/no or n/a>
| Completion |  | <yes/no or n/a>
Construction | FTA grant application in TrAMS |  | <yes/no or n/a> |  |  | Copy of application (O) | <Enter temporary grant # here>
CON federally-funded | FHWA to FTA transfer request to IDOT |  | <yes/no or n/a> |  |  | Copy of request letter (R)
| FTA grant approval |  | <yes/no or n/a> |  |  |  | <Enter FTA grant # here>
| Contractor selection |  | <yes/no or n/a>
| Notice to proceed |  | <yes/no or n/a>
| Constuction started |  | <yes/no or n/a>
| Construction completed |  | <yes/no or n/a>
| FTA grant closed |  | <yes/no or n/a>
Other project activities | Funding announcement/press release |  | <yes/no or n/a>
| Ground-breaking event |  | <yes/no or n/a>
| Ribbon-cutting event |  | <yes/no or n/a>
| <enter activity> |  | <yes/no or n/a>
| <enter activity> |  | <yes/no or n/a>
| <enter activity> |  | <yes/no or n/a>
| <enter activity> |  | <yes/no or n/a>

## drop-down values
Dropdown: CA (cell H4) | Dropdown: CAStat (cell H4) | Dropdown: LetType (cell H5) | General |  | Dropdown: EnvApproval (cell H7)
<class of action> | <status> | <type> | <yes/no or n/a> | <yes/no> | <environmental approval type>
Class 1: Env. Impact Statement (EIS) | Anticipated | State | Yes | Yes | FONSI
Class 2: Categorical Exclusion (CE) | Approved | Local | No | No | ROD
Class 3: Environmental Assessment (EA) |  |  | N/A